## ReEngineering Progress
NO | PROJECT TYPE | SITE_ID | SITE MOVING STATUS | FINAL SITE ID | SITE-SECTOR (FINAL) | SECTOR | FILTER PER SECTOR | REGION | NE_ID | SITE_NAME | TP NAME | IOMS REGISTERED | PERMIT STATUS | ISSUE PROBLEM | NOTE PROBLEM | SEND PERMIT FORMAT | IMPLEMENTASI STATUS | Tanggal RFS | TEAM | SUBMIT IOMS | TEAM ONSITE STATUS | ISSUE IMPLEMENTASI | NOTE IMPLEMENTASI | STATUS ATP | NOTE FOTO EVIDENCE | PDID | SOW ID | PO ID | TIKET NUMBER | SEND FORMAT | PRIO CAPEX FINAL | NEW STATUS IMPLEMENTATION | PRIO | LATITUDE | LONGITUDE | FILE DATE | PO BULAN
1 | FILTERING | CLG020 | Fix | CLG020 | CLG020-2 | 2 | 1 | R03 Jakarta & Banten | CLG020MT1 | E_CLG020_Cilegon4 | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-14 | Denny Suhendra | Done | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03231732 | R0011058250 | 4200052176 | ATP000000282692 | #NAME? | Batch#2 | 02. FFT Scan Done, Continue | P3 | -6.0241 | 106.069 | 2026-03-09 | 3
2 | FILTERING | CLG036 | Fix | CLG036 | CLG036-2 | 2 | 1 | R03 Jakarta & Banten | CLG036MT1 | E_CLG036_Banjarnegara-IND | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-19 | Denny Suhendra | Done | ONSITE |  |  | TAGGING DONE | Complate | NEED PDID | R0013075459 | 9372/TC.03/EN-01/XI/2025 | ATP000000278733 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.0424 | 105.9847 | 2026-03-09 | 3
3 | FILTERING | CLG071 | Fix | CLG071 | CLG071-1 | 1 | 1 | R03 Jakarta & Banten | CLG071MT1 | E_CLG071_Karangasemcilegon-PTI | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-04 | Denny Suhendra | Done | ONSITE |  | Tidak bisa create permit karena sistemnya error. Sudah lapor ke helpdesk nya INEOM untuk di perbaikin sejak 24 Feb namun sampai hari ini masih error | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235445 | R0013075435 | 9372/TC.03/EN-01/XI/2025 | ATP000000278556 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.0375 | 106.0564 | 2026-04-17 | 4
4 | FILTERING | CLG115 | Fix | CLG115 | CLG115-1 | 1 | 2 | R03 Jakarta & Banten | CLG115MT1 | E_CLG115_Bendungancilegon-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-16 | Denny Suhendra | Done | ONSITE |  |  | READY REVIEW | Complate | R03231733 | R0011058231 | 4200052176 | ATP000000282668 | #NAME? | Batch#2 | 02. FFT Scan Done, Continue | P2 | -6.034 | 106.0506 | 2026-03-09 | 3
5 | FILTERING | CLG117 | Fix | CLG117 | CLG117-1 | 1 | 1 | R03 Jakarta & Banten | CLG117MT1 | E_CLG117M41_Kampungciporong-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-11 | Denny Suhendra | Done | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0022633078 | 5992/TC.03/EN-01/IV/2026 | ATP000000288425 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | -5.9401 | 106.0604 | 2026-04-17 | 4
6 | FILTERING | CLG117 | Fix | CLG117 | CLG117-2 | 2 | 2 | R03 Jakarta & Banten | CLG117MT1 | E_CLG117M41_Kampungciporong-DMT | DMT | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Pindah File Site List 8 April 2026, Not register IOMS | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P2 | -5.9401 | 106.0604 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
7 | FILTERING | JKS184 | Fix | JKS184 | JKS184-3 | 3 | 2 | R03 Jakarta & Banten | JKS184MT1 | JKS184-DEWISARTIKA-MACRO | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-02-19 | Nusa Satria Wibowo |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0011058349 | 4200052176 | ATP000000277080 | #NAME? | Batch#2 | 02. FFT Scan Done, Continue |  | -6.2525 | 106.8645 | 2026-03-09 | 2
8 | FILTERING | JKS991 | Fix | JKS991 | JKS991-1 | 1 | 1 | R03 Jakarta & Banten | JKS991MT1 | JKS991-LTNGAGUNGFLX-MACRO | TBG | Registered | 5. Permit Released | 1. NO ISSUE | Existing filter lama tetep dipasang | #NAME? | RFS | 2026-02-21 | Nusa Satria Wibowo |  | ONSITE |  | CAF TBG, Existing filter lama | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03231702 | R0011058391 | 4200052176 | ATP000000277911 | #NAME? | Batch#2 | 02. FFT Scan Done, Continue |  | -6.3437 | 106.8302 | 2026-03-09 | 2
9 | FILTERING | JKT397 | Fix | JKT397 | JKT397-1 | 1 | 2 | R03 Jakarta & Banten | JKT397MT1 | E_JKT397M41_BkncawangINDOOR | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-02-27 | Nusa Satria Wibowo |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Re-Tagging Foto, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232924 | R0009678772 | 4200052273 | ATP000000277912 | #NAME? | Batch#2 | 02. FFT Scan Done, Continue |  | -6.2587 | 106.868 | 2026-03-09 | 2
10 | FILTERING | JTX540 | Fix | JTX540 | JTX540-3 | 3 | 1 | R03 Jakarta & Banten | JTX540MT1 | JTX540-PERMANENCOMBATPASARKRAMATDJATI-PTI-MACRO | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-02-25 | Nusa Satria Wibowo |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232938 | R0009678886 | 4200052273 | ATP000000277094 | #NAME? | Batch#2 | 02. FFT Scan Done, Continue |  | -6.2951 | 106.8699 | 2026-03-09 | 2
11 | FILTERING | PDG116 | Fix | PDG116 | PDG116-1 | 1 | 1 | R03 Jakarta & Banten | PDG116MT1 | E_PDG116_Desakadubale-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-05-04 | Denny Suhendra |  | ONSITE |  | Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03232642 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.3513 | 106.1103 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
12 | FILTERING | PDG116 | Fix | PDG116 | PDG116-3 | 3 | 1 | R03 Jakarta & Banten | PDG116MT1 | E_PDG116_Desakadubale-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-05-04 | Denny Suhendra |  | ONSITE |  | Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03232642 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.3513 | 106.1103 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
13 | FILTERING | PDG117 | Fix | PDG117 | PDG117-1 | 1 | 1 | R03 Jakarta & Banten | PDG117MT1 | E_PDG117_JlrayamalimpingSTPM | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | NEED PDID | R0013075276 | 9372/TC.03/EN-01/XI/2025 | ATP000000279299 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.4545 | 105.9934 | 2026-03-09 | 3
14 | FILTERING | PDG117 | Fix | PDG117 | PDG117-2 | 2 | 1 | R03 Jakarta & Banten | PDG117MT1 | E_PDG117_JlrayamalimpingSTPM | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | NEED PDID | R0013075276 | 9372/TC.03/EN-01/XI/2025 | ATP000000279299 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.4545 | 105.9934 | 2026-03-09 | 3
15 | FILTERING | PDG621 | Fix | PDG621 | PDG621-1 | 1 | 1 | R03 Jakarta & Banten | PDG621MT1 | E_PDG621_Wrkasbinuang | DMT | Registered | 1. Planning | NEED CAF | NEED CAF (DMT - STP) | #NAME? | Planning | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03232641 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1128 | 106.3349 | 2026-04-17 | 3
16 | FILTERING | PDG639 | Fix | PDG639 | PDG639-1 | 1 | 1 | R03 Jakarta & Banten | PDG639MT1 | E_PDG639_Cibodaspdg | DMT | Registered | 6. Expired Permit | PERMIT ISSUE | Tim belum terdaftar di Web CMI | #NAME? | Planning | [6 empty] | AWAITING DATA |  | R03232013 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.3934 | 106.101 | 2026-04-17 | 2
17 | FILTERING | PDG639 | Fix | PDG639 | PDG639-2 | 2 | 1 | R03 Jakarta & Banten | PDG639MT1 | E_PDG639_Cibodaspdg | DMT | Registered | 6. Expired Permit | PERMIT ISSUE | Tim belum terdaftar di Web CMI | #NAME? | Planning | [6 empty] | AWAITING DATA | Tagging Issue | R03232013 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.3934 | 106.101 | 2026-04-17 | 3
18 | FILTERING | RKB010 | Fix | RKB010 | RKB010-2 | 2 | 1 | R03 Jakarta & Banten | RKB010MT1 | E_RKB010_Cikulur | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-31 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | NEED PDID | R0013075181 | 9372/TC.03/EN-01/XI/2025 | ATP000000278728 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.3885 | 106.1472 | 2026-03-09 | 3
19 | FILTERING | RKB026 | Fix | RKB026 | RKB026-3 | 3 | 1 | R03 Jakarta & Banten | RKB026MT1 | E_RKB026_Muarabngmlm2 | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-17 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0009678919 | 4200052273 | ATP000000266036 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.8006 | 105.928 | 2026-04-17 | 4
20 | FILTERING | RKB641 | Fix | RKB641 | RKB641-3 | 3 | 1 | R03 Jakarta & Banten | RKB641MT1 | E_RKB641_Cigoongutrnw | STP | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.4063 | 106.168 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
21 | FILTERING | RKB821 | Fix | RKB821 | RKB821-1 | 1 | 1 | R03 Jakarta & Banten | RKB821MT1 | E_RKB821_Parungsari-CMI | CMI | Registered | 1. Planning | PERMIT ISSUE | Tim tidak bisa terdaftar di CMI Group | #NAME? | Planning | [6 empty] | AWAITING DATA | TAGGING ISSUE | R03232017 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.3843 | 106.3365 | 2026-04-17 | 2
22 | FILTERING | RKB821 | Fix | RKB821 | RKB821-3 | 3 | 1 | R03 Jakarta & Banten | RKB821MT1 | E_RKB821_Parungsari-CMI | CMI | Registered | 1. Planning | PERMIT ISSUE | Tim tidak bisa terdaftar di CMI Group | #NAME? | Planning | [6 empty] | AWAITING DATA |  | R03232017 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.3843 | 106.3365 | 2026-04-17 | 2
23 | FILTERING | SKB611 | Fix | SKB611 | SKB611-2 | 2 | 1 | R03 Jakarta & Banten | SKB611MT1 | E_SKB611M41_Bayahlebak | TSL | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | Planning | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.9418 | 106.2569 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
24 | FILTERING | SRG015 | Fix | SRG015 | SRG015-1 | 1 | 1 | R03 Jakarta & Banten | SRG015MT1 | E_SRG015_Tamankrakataucilegon-EBT | EBT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-06 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235439 | R0013075429 | 9372/TC.03/EN-01/XI/2025 | ATP000000278549 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.0613 | 106.072 | 2026-04-17 | 4
25 | FILTERING | SRG015 | Fix | SRG015 | SRG015-3 | 3 | 1 | R03 Jakarta & Banten | SRG015MT1 | E_SRG015M41_Tamankrakataucilegon-EBT | EBT | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03235439 |  |  |  | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P2 | -6.0613 | 106.072 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
26 | FILTERING | SRG029 | Fix | SRG029 | SRG029-1 | 1 | 1 | R03 Jakarta & Banten | SRG029MT1 | E_SRG029_Cikandegabus | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-18 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232629 | R0009678920 | 4200052273 | ATP000000282695 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2101 | 106.364 | 2026-04-17 | 3
27 | FILTERING | SRG031 | Fix | SRG031 | SRG031-3 | 3 | 1 | R03 Jakarta & Banten | SRG031MT1 | E_SRG031_Carenang | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-01 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | NEED PDID | R0013075019 | 9372/TC.03/EN-01/XI/2025 | ATP000000278751 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.0908 | 106.3234 | 2026-03-09 | 3
28 | FILTERING | SRG067 | Fix | SRG067 | SRG067-1 | 1 | 1 | R03 Jakarta & Banten | SRG067MT1 | E_SRG067_Sepangsrg | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-01 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | NEED PDID | R0013075028 | 9372/TC.03/EN-01/XI/2025 | ATP000000278551 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1345 | 106.1343 | 2026-04-17 | 3
29 | FILTERING | TGR130 | Moving | SRG113 | SRG113-1 | 2 | 1 | R03 Jakarta & Banten | TGR130MT1 | SRG113MT1_Waringinkurung-DMT_MT01 | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-14 | Denny Suhendra |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232627 | R0000604629 | 9295/TC.03/EN-01/X/2024 | ATP000000282700 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.06 | 106.0656 | 2026-04-17 | 3
30 | FILTERING | SRG135 | Fix | SRG135 | SRG135-3 | 3 | 1 | R03 Jakarta & Banten | SRG135MT1 | E_SRG135_Bantentv | NMM | Registered | 1. Planning | PERMIT ISSUE | TI mencari kontak TP | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1241 | 106.1872 | 2026-04-17 | 3
31 | FILTERING | SRG162 | Fix | SRG162 | SRG162-3 | 3 | 1 | R03 Jakarta & Banten | SRG162MT1 | E_SRG162M41_Serangtimur2-TBG | TBG | Not Registered | 9. Cancelled | NEED CAF | NEED CAF / BELUM ADA DI IOMS | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.1216 | 106.1934 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
32 | FILTERING | SRG192 | Fix | SRG192 | SRG192-2 | 2 | 1 | R03 Jakarta & Banten | SRG192MT1 | E_SRG192_Mlngnengh-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-16 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232624 | R0009678922 | 4200052273 | ATP000000282701 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2151 | 106.17 | 2026-03-09 | 3
33 | FILTERING | SRG207 | Fix | SRG207 | SRG207-2 | 2 | 1 | R03 Jakarta & Banten | SRG207MT | SRG207-PASULUHANWALANTAKADMT-MACRO | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-13 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0021933181 | 4200055400 | ATP000000288524 | #NAME? | Batch 4 & 5 | 02. FFT Scan Done, Continue |  | -6.1684 | 106.2275 | 2026-04-17 | 4
35 | FILTERING | SRG210 | Fix | SRG210 | SRG210-2 | 2 | 1 | R03 Jakarta & Banten | SRG210MT1 | E_SRG210M41_Mesjidpriyayikasemen-DMT | DMT | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.0845 | 106.1972 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
36 | FILTERING | SRG210 | Fix | SRG210 | SRG210-3 | 3 | 1 | R03 Jakarta & Banten | SRG210MT1 | E_SRG210M41_Mesjidpriyayikasemen-DMT | DMT | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.0845 | 106.1972 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
37 | FILTERING | SRG229 | Fix | SRG229 | SRG229-1 | 1 | 1 | R03 Jakarta & Banten | SRG229MT1 | E_SRG229M41_Gelamtaktakan-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.156 | 106.1258 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
38 | FILTERING | SRG229 | Fix | SRG229 | SRG229-2 | 2 | 1 | R03 Jakarta & Banten | SRG229MT1 | E_SRG229M41_Gelamtaktakan-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.156 | 106.1258 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
39 | FILTERING | SRG229 | Fix | SRG229 | SRG229-3 | 3 | 1 | R03 Jakarta & Banten | SRG229MT1 | E_SRG229M41_Gelamtaktakan-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.156 | 106.1258 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
40 | FILTERING | SRG271 | Fix | SRG271 | SRG271-3 | 3 | 1 | R03 Jakarta & Banten | SRG271MT1 | E_SRG271_Katulisancikeusal-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-29 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232623 | R0009678914 | 4200052273 | ATP000000282702 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2361 | 106.2831 | 2026-04-17 | 3
41 | FILTERING | SRG277 | Fix | SRG277 | SRG277-1 | 1 | 1 | R03 Jakarta & Banten | SRG277MT1 | E_SRG277M41_Melatiwaringinkurung-PST | PST | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.0851 | 106.0559 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
42 | FILTERING | SRG277 | Fix | SRG277 | SRG277-2 | 2 | 1 | R03 Jakarta & Banten | SRG277MT1 | E_SRG277M41_Melatiwaringinkurung-PST | PST | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.0851 | 106.0559 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
43 | FILTERING | SRG277 | Fix | SRG277 | SRG277-3 | 3 | 1 | R03 Jakarta & Banten | SRG277MT1 | E_SRG277M41_Melatiwaringinkurung-PST | PST | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.0851 | 106.0559 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
44 | FILTERING | SRG282 | Fix | SRG282 | SRG282-1 | 1 | 1 | R03 Jakarta & Banten | SRG282MT1 | E_SRG282M41_Gunungsugihanyer-PST | PST | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.0595 | 105.9367 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
45 | FILTERING | JTX676 | Moving | SRG617 | SRG617-3 | 1 | 1 | R03 Jakarta & Banten | JTX676MT1 | E_JTX676_Pertaminacakung-TBG | TBG | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | Planning |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.4905 | 106.3545 | 2026-04-17 | 3
46 | FILTERING | SRG618 | Fix | SRG618 | SRG618-1 | 1 | 1 | R03 Jakarta & Banten | SRG618MT1 | E_SRG618_Termnlserang | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Denny Suhendra |  | ONSITE |  | Yang di install sector 1,2,3 | READY REVIEW | Complate | NEED PDID | R0013075299 | 9372/TC.03/EN-01/XI/2025 | ATP000000282174 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P1 | -6.1214 | 106.1793 | 2026-03-09 | 3
47 | FILTERING | SRG618 | Fix | SRG618 | SRG618-2 | 2 | 1 | R03 Jakarta & Banten | SRG618MT1 | E_SRG618_Termnlserang | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Denny Suhendra |  | ONSITE |  | Yang di install sector 1,2,3 | READY REVIEW | Complate | NEED PDID | R0013075299 | 9372/TC.03/EN-01/XI/2025 | ATP000000282174 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P1 | -6.1214 | 106.1793 | 2026-03-09 | 3
48 | FILTERING | SRG618 | Fix | SRG618 | SRG618-3 | 3 | 1 | R03 Jakarta & Banten | SRG618MT1 | E_SRG618_Termnlserang | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Denny Suhendra |  | ONSITE |  | Yang di install sector 1,2,3 | READY REVIEW | Complate | NEED PDID | R0013075299 | 9372/TC.03/EN-01/XI/2025 | ATP000000282174 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P1 | -6.1214 | 106.1793 | 2026-03-09 | 3
49 | FILTERING | SRG648 | Fix | SRG648 | SRG648-1 | 1 | 1 | R03 Jakarta & Banten | SRG648MT1 | E_SRG648_Kranjung | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-12 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232024 | R0013074968 | 9372/TC.03/EN-01/XI/2025 | ATP000000278750 | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.1383 | 106.282 | 2026-03-09 | 3
50 | FILTERING | SRG648 | Fix | SRG648 | SRG648-3 | 3 | 1 | R03 Jakarta & Banten | SRG648MT1 | E_SRG648_Kranjung | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-12 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232024 | R0013074968 | 9372/TC.03/EN-01/XI/2025 | ATP000000278750 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.1383 | 106.282 | 2026-03-09 | 3
51 | FILTERING | SRG652 | Fix | SRG652 | SRG652-3 | 3 | 1 | R03 Jakarta & Banten | SRG652MT1 | E_SRG652_Serbucikande | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-29 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232025 | R0008297238 | 4200052217 | ATP000000259773 | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P3 | -6.1964 | 106.3361 | 2026-04-17 | 3
52 | FILTERING | SRG656 | Fix | SRG656 | SRG656-2 | 2 | 1 | R03 Jakarta & Banten | SRG656MT1 | E_SRG656_Cilegoncity | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-30 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232621 | R0009678923 | 4200052273 | ATP000000283305 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.0204 | 106.062 | 2026-04-17 | 3
53 | FILTERING | SRG671 | Fix | SRG671 | SRG671-1 | 1 | 2 | R03 Jakarta & Banten | SRG671MT1 | E_SRG671_Terasbendung | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-06 | Denny Suhendra |  | ONSITE |  | Site SRG671 merupakan reseller CMI namun tidak ada di website nya CMI. Sedang di cari solusi nya oleh pihak TI | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235182 | R0013075170 | 9372/TC.03/EN-01/XI/2025 | ATP000000278552 | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P1 | -6.0911 | 106.2858 | 2026-03-09 | 3
54 | FILTERING | SRG671 | Fix | SRG671 | SRG671-2 | 2 | 2 | R03 Jakarta & Banten | SRG671MT1 | E_SRG671_Terasbendung | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-06 | Denny Suhendra |  | ONSITE |  | Site SRG671 merupakan reseller CMI namun tidak ada di website nya CMI. Sedang di cari solusi nya oleh pihak TI | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235182 | R0013075170 | 9372/TC.03/EN-01/XI/2025 | ATP000000278552 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P1 | -6.0911 | 106.2858 | 2026-03-09 | 3
55 | FILTERING | SRG677 | Fix | SRG677 | SRG677-3 | 3 | 1 | R03 Jakarta & Banten | SRG677MT | Pgandikan-NMM | STP | Registered | 1. Planning | NEED CAF | NEED CAF | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch 4 & 5 | 02. FFT Scan Done, Continue |  | -6.0677 | 106.305 | 2026-04-17 | 4
56 | FILTERING | SRG683 | Fix | SRG683 | SRG683-1 | 1 | 1 | R03 Jakarta & Banten | SRG683MT | E_SRG683_Bendungbt-PTI | PTI | Registered | 1. Planning | NEED CAF | NEED CAF | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.0953 | 106.207 | 2026-04-17 | 4
57 | FILTERING | SRG720 | Fix | SRG720 | SRG720-1 | 1 | 1 | R03 Jakarta & Banten | SRG720MT1 | E_SRG720_Situcikande-NMM | NMM | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | Planning | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.2141 | 106.3413 | 2026-04-17 | 3
58 | FILTERING | SRG720 | Fix | SRG720 | SRG720-3 | 3 | 1 | R03 Jakarta & Banten | SRG720MT1 | E_SRG720_Situcikande-NMM | NMM | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.2141 | 106.3413 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
59 | FILTERING | SRG739 | Fix | SRG739 | SRG739-2 | 2 | 1 | R03 Jakarta & Banten | SRG739MT1 | E_SRG739M41_Cilegonindah-DMT | DMT | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.0431 | 106.0689 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
60 | FILTERING | SRG741 | Fix | SRG741 | SRG741-2 | 2 | 1 | R03 Jakarta & Banten | SRG741MT | E_SRG741_Drangong-TBG | TBG | Registered | 1. Planning | NEED CAF | NEED CAF | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.1042 | 106.135 | 2026-04-17 | 4
61 | FILTERING | SRG743 | Fix | SRG743 | SRG743-2 | 2 | 1 | R03 Jakarta & Banten | SRG743MT1 | E_SRG743_Sepang-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-17 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232619 | R0009678924 | 4200052273 | ATP000000266044 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1302 | 106.14 | 2026-04-17 | 3
62 | FILTERING | SRG758 | Fix | SRG758 | SRG758-2 | 2 | 1 | R03 Jakarta & Banten | SRG758MT1 | E_SRG758_Lebaksiligempol-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE | CAF Rilis | #NAME? | RFS | 2026-04-23 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232027 | R0008297237 | 4200052217 | ATP000000259783 | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P3 | -6.0949 | 106.1703 | 2026-04-17 | 4
63 | FILTERING | SRG771 | Fix | SRG771 | SRG771-2 | 2 | 1 | R03 Jakarta & Banten | SRG771MT1 | E_SRG771_Pabuaranbelungan-NMM | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-11 | Denny Suhendra |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235178 | R0013075166 | 9372/TC.03/EN-01/XI/2025 | ATP000000278727 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1434 | 106.2662 | 2026-03-09 | 3
64 | FILTERING | SRG794 | Fix | SRG794 | SRG794-1 | 1 | 1 | R03 Jakarta & Banten | SRG794MT1 | E_SRG794_Karetsepatan-PTI | PTI | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.138 | 106.5768 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
65 | FILTERING | SRG836 | Fix | SRG836 | SRG836-2 | 2 | 1 | R03 Jakarta & Banten | SRG836MT | E_SRG836_Tenjoayu-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-13 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0021933176 | 4200055400 | ATP000000288526 | #NAME? | Batch 4 & 5 | 02. FFT Scan Done, Continue |  | -6.0019 | 106.345 | 2026-04-17 | 4
66 | FILTERING | SRG837 | Fix | SRG837 | SRG837-2 | 2 | 1 | R03 Jakarta & Banten | SRG837MT1 | E_SRG837M41_Harjataniclg-GTI | GTI | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.0408 | 106.082 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
67 | FILTERING | SRG840 | Fix | SRG840 | SRG840-3 | 3 | 1 | R03 Jakarta & Banten | SRG840MT1 | E_SRG840_Bojongsukadalem-PTI | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | NEED PDID | R0013075397 | 9372/TC.03/EN-01/XI/2025 | ATP000000279297 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.0573 | 106.0792 | 2026-03-09 | 3
68 | FILTERING | SRG862 | Fix | SRG862 | SRG862-2 | 2 | 1 | R03 Jakarta & Banten | SRG862MT1 | E_SRG862_Srgcityutara-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-17 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232617 | R0009678925 | 4200052273 | ATP000000283307 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1066 | 106.1646 | 2026-03-09 | 3
69 | FILTERING | SRG905 | Fix | SRG905 | SRG905-1 | 1 | 1 | R03 Jakarta & Banten | SRG905MT1 | E_SRG905_Kendayakankragilan-TBG | DMT | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03232028 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.1512 | 106.2751 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
70 | FILTERING | SRG905 | Fix | SRG905 | SRG905-3 | 3 | 1 | R03 Jakarta & Banten | SRG905MT1 | E_SRG905_Kendayakankragilan-TBG | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-02 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232028 | R0013074638 | 9372/TC.03/EN-01/XI/2025 | ATP000000278550 | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.1512 | 106.2751 | 2026-04-17 | 4
71 | FILTERING | SRG907 | Fix | SRG907 | SRG907-1 | 1 | 1 | R03 Jakarta & Banten | SRG907MT1 | E_SRG907_Situteratecikande-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-18 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232614 | R0013075377 | 9372/TC.03/EN-01/XI/2025 | ATP000000278555 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.2189 | 106.3469 | 2026-03-09 | 3
72 | FILTERING | SRG907 | Fix | SRG907 | SRG907-2 | 2 | 1 | R03 Jakarta & Banten | SRG907MT1 | E_SRG907_Situteratecikande-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-18 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232614 | R0013075377 | 9372/TC.03/EN-01/XI/2025 | ATP000000278555 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.2189 | 106.3469 | 2026-04-17 | 3
73 | FILTERING | SRG912 | Fix | SRG912 | SRG912-2 | 2 | 1 | R03 Jakarta & Banten | SRG912MT1 | E_SRG912_Cijerukkibin-DMT | DMT | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain [ATP] | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1858 | 106.3182 | 2026-04-17 | 3
74 | FILTERING | SRG933 | Fix | SRG933 | SRG933-1 | 1 | 1 | R03 Jakarta & Banten | SRG933MT1 | E_SRG933M41_Mekarsaricinangkabo-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P2 | -6.1363 | 105.9046 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
75 | FILTERING | SRG933 | Fix | SRG933 | SRG933-3 | 3 | 1 | R03 Jakarta & Banten | SRG933MT1 | E_SRG933M41_Mekarsaricinangkabo-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P2 | -6.1363 | 105.9046 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
76 | FILTERING | SRG938 | Fix | SRG938 | SRG938-3 | 3 | 1 | R03 Jakarta & Banten | SRG938MT1 | E_SRG938_Sukaramecikeusalbo-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-11 | Denny Suhendra |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235223 | R0013075211 | 9372/TC.03/EN-01/XI/2025 | ATP000000279294 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1941 | 106.2489 | 2026-03-09 | 3
77 | FILTERING | SRG939 | Fix | SRG939 | SRG939-1 | 1 | 1 | R03 Jakarta & Banten | SRG939MT1 | E_SRG939M41_Cinangkaserangbo-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.1581 | 105.8742 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
78 | FILTERING | SRG939 | Fix | SRG939 | SRG939-2 | 2 | 1 | R03 Jakarta & Banten | SRG939MT1 | E_SRG939M41_Cinangkaserangbo-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.1581 | 105.8742 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
79 | FILTERING | SRG939 | Fix | SRG939 | SRG939-3 | 3 | 1 | R03 Jakarta & Banten | SRG939MT1 | E_SRG939M41_Cinangkaserangbo-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.1581 | 105.8742 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
80 | FILTERING | SRG944 | Fix | SRG944 | SRG944-1 | 1 | 1 | R03 Jakarta & Banten | SRG944MT | E_SRG944_Cidahukopo-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE | CAF Release | #NAME? | RFS | 2026-05-05 | Denny Suhendra |  | ONSITE |  |  | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2906 | 106.3807 | 2026-04-17 | 4
81 | FILTERING | SRG944 | Fix | SRG944 | SRG944-2 | 2 | 1 | R03 Jakarta & Banten | SRG944MT | E_SRG944_Cidahukopo-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-05-05 | Denny Suhendra |  | ONSITE |  |  | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2906 | 106.3807 | 2026-04-17 | 4
82 | FILTERING | SRG954 | Fix | SRG954 | SRG954-2 | 2 | 1 | R03 Jakarta & Banten | SRG954MT1 | E_SRG954_Petirserangbo-TBG | TBG | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain [ATP] | #NAME? | Cancelled | [6 empty] | AWAITING DATA |  | R03232029 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.2199 | 106.2066 | 2026-04-17 | 2
83 | FILTERING | SRG954 | Fix | SRG954 | SRG954-3 | 3 | 1 | R03 Jakarta & Banten | SRG954MT1 | E_SRG954_Petirserangbo-TBG | TBG | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain [ATP] | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03232029 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.2199 | 106.2066 | 2026-04-17 | 2
84 | FILTERING | TGR001 | Fix | TGR001 | TGR001-1 | 1 | 1 | R03 Jakarta & Banten | TGR001MT1 | C_TGR001M41_Rajegsukamanah-STP | STP | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.1221 | 106.5214 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
85 | FILTERING | TGR010 | Fix | TGR010 | TGR010-2 | 2 | 1 | R03 Jakarta & Banten | TGR010MT1 | E_TGR010_Jlindustriraya-PTI | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1898 | 106.5513 | 2026-04-17 | 3
86 | FILTERING | TGR013 | Fix | TGR013 | TGR013-1 | 1 | 2 | R03 Jakarta & Banten | TGR013MT1 | E_TGR013_Kedatontangerang-DMT | DMT | Registered | 1. Planning | NEED CAF | NEED CAF (DMT - EMA) | #NAME? | Planning | [5 empty] | tidak bisa create permit karena sistemnya error. Sudah lapor ke helpdesk nya INEOM untuk di perbaiki sejak 24 Feb namun sampai hari ini masih error | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.1872 | 106.5268 | 2026-04-17 | 3
87 | FILTERING | TGR016 | Fix | TGR016 | TGR016-3 | 3 | 1 | R03 Jakarta & Banten | TGR016MT1 | E_TGR016M41_Pagedangan-PTI | PTI | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.2955 | 106.6279 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
88 | FILTERING | TGR020 | Fix | TGR020 | TGR020-1 | 1 | 1 | R03 Jakarta & Banten | TGR020MT1 | E_TGR020_Rayacurug-DMT | DMT | Registered | 1. Planning | NEED CAF | NEED CAF (DMT - EMA) | #NAME? | Planning | [6 empty] | AWAITING DATA |  | R03232611 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2665 | 106.558 | 2026-04-17 | 3
89 | FILTERING | TGR034 | Fix | TGR034 | TGR034-1 | 1 | 1 | R03 Jakarta & Banten | TGR034MT1 | C_TGR034M41_Bojongrengattangerang-PTI | PTI | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P2 | -6.1055 | 106.6416 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
90 | FILTERING | TGR034 | Fix | TGR034 | TGR034-2 | 2 | 1 | R03 Jakarta & Banten | TGR034MT1 | C_TGR034M41_Bojongrengattangerang-PTI | PTI | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P2 | -6.1055 | 106.6416 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
91 | FILTERING | TGR036 | Fix | TGR036 | TGR036-3 | 3 | 1 | R03 Jakarta & Banten | TGR036MT1 | E_TGR036_Boulevardutara-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-28 | Denny Suhendra |  | ONSITE |  |  | READY REVIEW | Complate | R03232609 | R0009678928 | 4200052273 | ATP000000283308 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2897 | 106.6402 | 2026-04-17 | 3
92 | FILTERING | TGR072 | Fix | TGR072 | TGR072-2 | 2 | 1 | R03 Jakarta & Banten | TGR072MT1 | E_TGR072_Kawasanindustrimekarjaya-DMT | TSL | Registered | 10. DROP OUT | TOWER ISSUE | Tidak bisa naik karena tiang monopole | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1427 | 106.5869 | 2026-04-17 | 3
93 | FILTERING | TGR094 | Fix | TGR094 | TGR094-1 | 1 | 1 | R03 Jakarta & Banten | TGR094MT1 | E_TGR094_Pasarkemis-STP | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-13 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0013074992 | 9372/TC.03/EN-01/XI/2025 | ATP000000280099 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1507 | 106.5329 | 2026-04-17 | 4
94 | FILTERING | TGR095 | Fix | TGR095 | TGR095-1 | 1 | 1 | R03 Jakarta & Banten | TGR095MT1 | E_TGR095_Pasarkemis2-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-03 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235236 | R0013075224 | 9372/TC.03/EN-01/XI/2025 | ATP000000280100 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1678 | 106.5401 | 2026-04-17 | 4
95 | FILTERING | TGR095 | Fix | TGR095 | TGR095-2 | 1 | 1 | R03 Jakarta & Banten | TGR095MT1 | E_TGR095_Pasarkemis2-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-13 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235236 | R0022633089 | 5992/TC.03/EN-01/IV/2026 | ATP000000288427 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P3 | -6.1678 | 106.5401 | 2026-04-17 | 4
96 | FILTERING | TGR100 | Fix | TGR100 | TGR100-3 | 3 | 1 | R03 Jakarta & Banten | TGR100MT | E_TGR100_Plpcurug-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-18 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0022633071 | 5992/TC.03/EN-01/IV/2026 | ATP000000288424 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2916 | 106.5867 | 2026-04-17 | 4
97 | FILTERING | TGR117 | Fix | TGR117 | TGR117-2 | 2 | 1 | R03 Jakarta & Banten | TGR117MT1 | E_TGR117_Tamanubudpermai-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-06 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235166 | R0013075154 | 9372/TC.03/EN-01/XI/2025 | ATP000000279298 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2334 | 106.5841 | 2026-03-09 | 3
98 | FILTERING | TGR118 | Fix | TGR118 | TGR118-1 | 1 | 1 | R03 Jakarta & Banten | TGR118MT1 | E_TGR118_Tamankutabumi-DMT | DMT | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.1561 | 106.5656 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
99 | FILTERING | TGR118 | Fix | TGR118 | TGR118-2 | 2 | 1 | R03 Jakarta & Banten | TGR118MT1 | E_TGR118_Tamankutabumi-DMT | DMT | Registered | 1. Planning | NEED CAF | NEED CAF (DMT-EMA) | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.1561 | 106.5656 | 2026-04-17 | 3
100 | FILTERING | TGR136 | Fix | TGR136 | TGR136-3 | 3 | 1 | R03 Jakarta & Banten | TGR136MT | Jalanserdangkulon-PTI | PTI | Registered | 1. Planning | TP ISSUE | AKSES WM | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch 4 & 5 | 02. FFT Scan Done, Continue |  | -6.2885 | 106.5524 | 2026-04-17 | 4
101 | FILTERING | TGR160 | Fix | TGR160 | TGR160-3 | 3 | 1 | R03 Jakarta & Banten | TGR160MT1 | E_TGR160_Karetmaukjayasepatan-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-03 | Denny Suhendra |  | ONSITE |  | tidak bisa create permit karena sistemnya error. Sudah lapor ke helpdesk nya INEOM untuk di perbaiki sejak 24 Feb namun sampai hari ini masih error | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235186 | R0013075174 | 9372/TC.03/EN-01/XI/2025 | ATP000000279292 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1282 | 106.5948 | 2026-04-17 | 4
102 | FILTERING | TGR170 | Fix | TGR170 | TGR170-3 | 3 | 1 | R03 Jakarta & Banten | TGR170MT | PERM_RAJEGMEKARSARI | TBG | Registered | 5. Permit Released | 1. NO ISSUE | CAF Rilis | #NAME? | RFS | 2026-04-27 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0021933168 | 4200055400 | ATP000000286309 | #NAME? | Batch 4 & 5 | 02. FFT Scan Done, Continue |  | -6.1283 | 106.5328 | 2026-04-17 | 4
103 | FILTERING | TGR177 | Fix | TGR177 | TGR177-1 | 1 | 1 | R03 Jakarta & Banten | TGR177MT1 | E_TGR177_Cihunilegok-STP | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-05 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2481 | 106.6136 | 2026-03-09 | 3
104 | FILTERING | TGR178 | Fix | TGR178 | TGR178-3 | 3 | 1 | R03 Jakarta & Banten | TGR178MT1 | E_TGR178_Hamsinbitung-DMT | DMT | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2215 | 106.5345 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
105 | FILTERING | TGR184 | Fix | TGR184 | TGR184-1 | 1 | 1 | R03 Jakarta & Banten | TGR184MT1 | E_TGR184_Villapermata-TBG | TBG | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.2218 | 106.584 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
106 | FILTERING | TGR184 | Fix | TGR184 | TGR184-2 | 2 | 1 | R03 Jakarta & Banten | TGR184MT1 | E_TGR184M41_Villapermata-TBG | TBG | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P2 | -6.2218 | 106.584 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
107 | FILTERING | TGR185 | Fix | TGR185 | TGR185-2 | 2 | 1 | R03 Jakarta & Banten | TGR185MT | E_TGR185_Kotatigaraksatangerang-DMT | DMT | Registered | 10. DROP OUT | TP ISSUE | Nama site sudah di takeout dari web DMT | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2422 | 106.4911 | 2026-04-17 | 4
108 | FILTERING | TGR189 | Fix | TGR189 | TGR189-3 | 3 | 1 | R03 Jakarta & Banten | TGR189MT1 | E_TGR220M41_Yepikresek-IBS | IBS | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1205 | 106.5807 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
109 | FILTERING | TGR206 | Fix | TGR206 | TGR206-3 | 3 | 1 | R03 Jakarta & Banten | TGR206MT | E_TGR206_Kpcikupa-TBG | TBG | Registered | 1. Planning | NEED CAF | NEED CAF | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2302 | 106.5122 | 2026-04-17 | 4
110 | FILTERING | TGR220 | Fix | TGR220 | TGR220-2 | 2 | 1 | R03 Jakarta & Banten | TGR220MT1 | E_TGR220M41_Yepikresek-IBS | IBS | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.1257 | 106.3802 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
111 | FILTERING | TGR227 | Fix | TGR227 | TGR227-3 | 3 | 1 | R03 Jakarta & Banten | TGR227HT1 | E_TGR227_IconbsdBTSH-IBS | UnKnown | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-09 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232042 | R0008297229 | 4200052217 | ATP000000259781 | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P3 | -6.3148 | 106.6478 | 2026-04-17 | 4
112 | FILTERING | TGR243 | Fix | TGR243 | TGR243-1 | 1 | 1 | R03 Jakarta & Banten | TGR243MT1 | E_TGR243_Sukabakticurug-PTI | PTI | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2526 | 106.5699 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
113 | FILTERING | TGR257 | Fix | TGR257 | TGR257-2 | 2 | 1 | R03 Jakarta & Banten | TGR257MT1 | E_TGR257_Siloamkelapadua-STP | STP | Registered | 1. Planning | NEED CAF | NEED CAF | #NAME? | Planning | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03232596 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2233 | 106.5966 | 2026-04-17 | 3
114 | FILTERING | TGR299 | Fix | TGR299 | TGR299-1 | 1 | 1 | R03 Jakarta & Banten | TGR299MT1 | E_TGR299_Industricikupatelaga-STP | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0013074985 | 9372/TC.03/EN-01/XI/2025 | ATP000000280102 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2179 | 106.506 | 2026-03-09 | 3
115 | FILTERING | TGR317 | Fix | TGR317 | TGR317-2 | 2 | 1 | R03 Jakarta & Banten | TGR317MT1 | E_TGR317_Cangkudubalarajapermai-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-27 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232592 | R0009678943 | 4200052273 | ATP000000283154 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1826 | 106.4581 | 2026-04-17 | 4
116 | FILTERING | TGR348 | Fix | TGR348 | TGR348-2 | 2 | 1 | R03 Jakarta & Banten | TGR348MT1 | E_TGR348_Bumiindahpsrkemis-DMT | DMT | Registered | 1. Planning | PERMIT ISSUE | CAF RILIS / TIM TIDAK BISA DI DAFTARIN PADA CMI GRUP | #NAME? | Planning | [6 empty] | AWAITING DATA |  | R03232591 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1702 | 106.5629 | 2026-04-17 | 3
117 | FILTERING | TGR356 | Fix | TGR356 | TGR356-1 | 1 | 1 | R03 Jakarta & Banten | TGR356MT1 | E_TGR356_Sukabakticurugtng-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-06 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2573 | 106.5766 | 2026-03-09 | 3
118 | FILTERING | TGR360 | Fix | TGR360 | TGR360-2 | 2 | 1 | R03 Jakarta & Banten | TGR360MT1 | E_TGR360M41_Kpcilongokpskemis-TBG | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.1728 | 106.5435 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
119 | FILTERING | TGR364 | Fix | TGR364 | TGR364-1 | 1 | 1 | R03 Jakarta & Banten | TGR364MT1 | E_TGR364M41_Sindangsaritangerang-DMT | DMT | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.1344 | 106.5349 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
120 | FILTERING | TGR364 | Fix | TGR364 | TGR364-2 | 2 | 1 | R03 Jakarta & Banten | TGR364MT1 | E_TGR364M41_Sindangsaritangerang-DMT | DMT | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.1344 | 106.5349 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
121 | FILTERING | TGR364 | Fix | TGR364 | TGR364-3 | 3 | 1 | R03 Jakarta & Banten | TGR364MT1 | E_TGR364M41_Sindangsaritangerang-DMT | DMT | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P1 | -6.1344 | 106.5349 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
122 | FILTERING | TGR365 | Fix | TGR365 | TGR365-2 | 2 | 1 | R03 Jakarta & Banten | TGR365MT1 | E_TGR365_Ptkasabitung-GTT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-29 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232589 | R0009678936 | 4200052273 | ATP000000282676 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.2312 | 106.5501 | 2026-04-17 | 3
123 | FILTERING | TGR365 | Fix | TGR365 | TGR365-3 | 3 | 1 | R03 Jakarta & Banten | TGR365MT1 | E_TGR365_Ptkasabitung-GTT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-29 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232589 | R0009678936 | 4200052273 | ATP000000282676 | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.2312 | 106.5501 | 2026-03-09 | 3
124 | FILTERING | JBX199 | Moving | TGR366 | TGR366-1 | 1 | 1 | R03 Jakarta & Banten | JBX199MT1 | E_JBX199_JlterataiBTSH-TBG | UnKnown | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#2 | 02. FFT Scan Done, Continue | P3 | -6.2374 | 106.5889 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
125 | FILTERING | TGR368 | Fix | TGR368 | TGR368-3 | 3 | 1 | R03 Jakarta & Banten | TGR368MT1 | E_TGR368_Ciffestcitraraya-BMS | TBS | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2302 | 106.5215 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
126 | FILTERING | TGR370 | Fix | TGR370 | TGR370-2 | 2 | 1 | R03 Jakarta & Banten | TGR370MT1 | E_TGR370_Bencongankelapadua-API | TBG | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2192 | 106.603 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
127 | FILTERING | TGR376 | Fix | TGR376 | TGR376-1 | 1 | 1 | R03 Jakarta & Banten | TGR376MT1 | E_TGR376_Sukadamaicikupa-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-29 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232587 | R0009678937 | 4200052273 | ATP000000282678 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.2179 | 106.5442 | 2026-04-17 | 3
128 | FILTERING | TGR376 | Fix | TGR376 | TGR376-2 | 2 | 1 | R03 Jakarta & Banten | TGR376MT1 | E_TGR376_Sukadamaicikupa-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-29 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232587 | R0009678937 | 4200052273 | ATP000000282678 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.2179 | 106.5442 | 2026-04-17 | 3
129 | FILTERING | TGR422 | Fix | TGR422 | TGR422-1 | 1 | 1 | R03 Jakarta & Banten | TGR422MT1 | E_TGR422_Jlpertaminatelagasari-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-02-27 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0013075044 | 9372/TC.03/EN-01/XI/2025 | ATP000000280103 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.217 | 106.5231 | 2026-04-17 | 2
130 | FILTERING | TGR463 | Fix | TGR463 | TGR463-2 | 2 | 2 | R03 Jakarta & Banten | TGR463MT1 | E_TGR463_Jlkpcrewed-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-24 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232585 | R0009678938 | 4200052273 | ATP000000283759 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.217 | 106.5385 | 2026-04-17 | 4
131 | FILTERING | TGR465 | Fix | TGR465 | TGR465-1 | 1 | 1 | R03 Jakarta & Banten | TGR465MT1 | E_TGR465_Jlbulakanbitung-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-12 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232045 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P2 | -6.2326 | 106.5447 | 2026-04-17 | 3
132 | FILTERING | TGR465 | Fix | TGR465 | TGR465-3 | 3 | 1 | R03 Jakarta & Banten | TGR465MT1 | E_TGR465_Jlbulakanbitung-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-12 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232045 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.2326 | 106.5447 | 2026-04-17 | 3
133 | FILTERING | TGR542 | Fix | TGR542 | TGR542-1 | 1 | 1 | R03 Jakarta & Banten | TGR542MT1 | E_TGR542_Rancagedegunungkaler-TBG | TBG | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.0894 | 106.3871 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
134 | FILTERING | TGR542 | Fix | TGR542 | TGR542-2 | 2 | 1 | R03 Jakarta & Banten | TGR542MT1 | E_TGR542_Rancagedegunungkaler-TBG | TBG | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.0894 | 106.3871 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
135 | FILTERING | TGR551 | Fix | TGR551 | TGR551-1 | 1 | 1 | R03 Jakarta & Banten | TGR551MT1 | E_TGR551_Talokkresek-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE | CAF Rilis | #NAME? | RFS | 2026-03-27 | Rizky Maulana Fridiansyah |  | ONSITE |  | Pindah File Site List 8 April 2026, | TAGGING ISSUE |  | R03235455 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.126 | 106.395 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
136 | FILTERING | TGR551 | Fix | TGR551 | TGR551-3 | 3 | 1 | R03 Jakarta & Banten | TGR551MT1 | E_TGR551_Talokkresek-TBG | TBG | Registered | 5. Permit Released | 1. NO ISSUE | CAF Rilis | #NAME? | RFS | 2026-03-27 | Rizky Maulana Fridiansyah |  | ONSITE |  | Pindah File Site List 8 April 2026, | TAGGING ISSUE |  | R03235455 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.126 | 106.395 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
137 | FILTERING | TGR577 | Fix | TGR577 | TGR577-1 | 1 | 1 | R03 Jakarta & Banten | TGR577MT1 | E_TGR577_Boulevardcitradenpasar-CMI | CMI | Registered | 1. Planning | PERMIT ISSUE | Tim tidak bisa terdaftar di CMI Group | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2515 | 106.511 | 2026-04-17 | 3
138 | FILTERING | TGR613 | Fix | TGR613 | TGR613-1 | 1 | 1 | R03 Jakarta & Banten | TGR613MT1 | TGR613_Sentiongteluknaga-PTI | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-07 | Denny Suhendra |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.05 | 106.6588 | 2026-04-17 | 4
139 | FILTERING | TNG004 | Fix | TNG004 | TNG004-1 | 1 | 1 | R03 Jakarta & Banten | TNG004MT1 | E_TNG004_Gandasari | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-03 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235283 | R0013075271 | 9372/TC.03/EN-01/XI/2025 | ATP000000280568 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2215 | 106.5616 | 2026-03-09 | 3
140 | FILTERING | TNG004 | Fix | TNG004 | TNG004-2 | 2 | 1 | R03 Jakarta & Banten | TNG004MT1 | E_TNG004_Gandasari | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-18 | Denny Suhendra |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235283 | R0022633062 | 5992/TC.03/EN-01/IV/2026 | ATP000000288423 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P3 | -6.2215 | 106.5616 | 2026-04-17 | 4
141 | FILTERING | TNG008 | Fix | TNG008 | TNG008-1 | 1 | 1 | R03 Jakarta & Banten | TNG008MT1 | E_TNG008_Balaraja | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03242379 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P1 | -6.2193 | 106.4411 | 2026-03-09 | 3
142 | FILTERING | TNG008 | Fix | TNG008 | TNG008-2 | 2 | 1 | R03 Jakarta & Banten | TNG008MT1 | E_TNG008_Balaraja | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03242379 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P1 | -6.2193 | 106.4411 | 2026-03-09 | 3
143 | FILTERING | TNG008 | Fix | TNG008 | TNG008-3 | 3 | 1 | R03 Jakarta & Banten | TNG008MT1 | E_TNG008_Balaraja | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-07 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03242379 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P1 | -6.2193 | 106.4411 | 2026-03-09 | 3
144 | FILTERING | TNG067 | Fix | TNG067 | TNG067-2 | 2 | 1 | R03 Jakarta & Banten | TNG067MT1 | E_TNG067_Klpduasrpng | TSL | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.241 | 106.6233 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
145 | FILTERING | TNG108 | Fix | TNG108 | TNG108-1 | 1 | 1 | R03 Jakarta & Banten | TNG108MT1 | E_TNG108_Villapmttgr | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03242387 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.2244 | 106.5883 | 2026-04-17 | 3
146 | FILTERING | TNG108 | Fix | TNG108 | TNG108-2 | 2 | 1 | R03 Jakarta & Banten | TNG108MT1 | E_TNG108_Villapmttgr | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03242387 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.2244 | 106.5883 | 2026-04-17 | 3
147 | FILTERING | TNG134 | Fix | TNG134 | TNG134-2 | 2 | 1 | R03 Jakarta & Banten | TNG134MT1 | E_TNG134_Mallkarawaci | DHOST | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-23 | Denny Suhendra |  | ONSITE |  | Pindah File Site List 8 April 2026, | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0009678953 | 4200052273 | ATP000000265340 | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2261 | 106.6059 | 2026-04-17 | 4
148 | FILTERING | TNG188 | Fix | TNG188 | TNG188-2 | 2 | 2 | R03 Jakarta & Banten | TNG188MT | E_TNG188_Kwindtrmnsbt | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-02 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue |  | -6.2186 | 106.5716 | 2026-03-09 | 3
149 | FILTERING | TNG189 | Fix | TNG189 | TNG189-1 | 1 | 1 | R03 Jakarta & Banten | TNG189MT1 | E_TNG189_Binongpermai | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | Planning | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2492 | 106.5752 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
150 | FILTERING | TNG197 | Fix | TNG197 | TNG197-3 | 3 | 1 | R03 Jakarta & Banten | TNG197MT1 | E_TNG197_Gdgserpong | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-05 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235047 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2687 | 106.6274 | 2026-03-09 | 3
151 | FILTERING | TNG257 | Fix | TNG257 | TNG257-1 | 1 | 2 | R03 Jakarta & Banten | TNG257MT1 | E_TNG257_Tamanubud | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-11 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232569 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P2 | -6.2334 | 106.5788 | 2026-03-09 | 3
152 | FILTERING | TNG328 | Fix | TNG328 | TNG328-1 | 1 | 1 | R03 Jakarta & Banten | TNG328MT1 | E_TNG328M41_Sindangjaya | TBG | Not Registered | 9. Cancelled | SITE-ID N/A IOMS |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.1398 | 106.5127 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
153 | FILTERING | TNG333 | Fix | TNG333 | TNG333-3 | 3 | 1 | R03 Jakarta & Banten | TNG333MT1 | E_TNG333_Ryserangkm12 | PTI | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.2228 | 106.5386 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
154 | FILTERING | TNG354 | Fix | TNG354 | TNG354-3 | 3 | 1 | R03 Jakarta & Banten | TNG354MT1 | E_TNG354_Palemrajarya | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-05 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2172 | 106.6062 | 2026-03-09 | 3
155 | FILTERING | TNG360 | Fix | TNG360 | TNG360-2 | 2 | 1 | R03 Jakarta & Banten | TNG360MT | E_TNG360M31_MalsumareconINDOOR | SMI | Registered | 1. Planning | NEED CAF | CAF Belum Reales | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue |  | -6.2414 | 106.6269 | 2026-04-17 | 3
156 | FILTERING | TNG383 | Fix | TNG383 | TNG383-3 | 3 | 1 | R03 Jakarta & Banten | TNG383MT1 | E_TNG383_Rayalegok-TBG | TBG | Registered | 10. DROP OUT | SITE ISSUE COMCASE | Comcase dan WM issue | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2499 | 106.6087 | 2026-04-17 | 3
157 | FILTERING | TNG409 | Fix | TNG409 | TNG409-1 | 1 | 1 | R03 Jakarta & Banten | TNG409MT1 | E_TNG409_Uphkarawaci-PWU | DHOST | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-25 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0013075022 | 9372/TC.03/EN-01/XI/2025 | ATP000000280571 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2286 | 106.6126 | 2026-04-17 | 4
158 | FILTERING | TNG508 | Fix | TNG508 | TNG508-2 | 2 | 1 | R03 Jakarta & Banten | TNG508MT1 | E_TNG508_Tigaraksa | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-03 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2857 | 106.4522 | 2026-03-09 | 3
159 | FILTERING | TNG512 | Fix | TNG512 | TNG512-2 | 2 | 1 | R03 Jakarta & Banten | TNG512MT | E_TNG512_Bitungjaya | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-02 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | NEEDS RETAGGING | Standarisasi Jumper, Re-Tagging Foto and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235081 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue |  | -6.2281 | 106.542 | 2026-03-09 | 3
160 | FILTERING | TNG533 | Fix | TNG533 | TNG533-3 | 3 | 1 | R03 Jakarta & Banten | TNG533MT1 | E_TNG533_Rajeg2 | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-03 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235415 |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.115 | 106.5193 | 2026-03-09 | 3
161 | FILTERING | TNG561 | Fix | TNG561 | TNG561-2 | 2 | 1 | R03 Jakarta & Banten | TNG561MT1 | E_TNG561_Asrodokan | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-03 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235460 | R0013075450 | 9372/TC.03/EN-01/XI/2025 | ATP000000280174 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1474 | 106.5689 | 2026-04-17 | 4
162 | FILTERING | TNG583 | Fix | TNG583 | TNG583-2 | 2 | 1 | R03 Jakarta & Banten | TNG583MT1 | E_TNG583_Bundercikupa | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-01 | Rizky Maulana Fridiansyah |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.1984 | 106.5433 | 2026-03-09 | 3
163 | FILTERING | TNG584 | Fix | TNG584 | TNG584-2 | 2 | 1 | R03 Jakarta & Banten | TNG584MT1 | E_TNG584_Cibugel | TSL | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P3 | -6.2536 | 106.4247 | 2026-03-09 | 2 | Tidak bisa dijalankan Karena harus memakai data terupdate
164 | FILTERING | TNG605 | Fix | TNG605 | TNG605-3 | 3 | 1 | R03 Jakarta & Banten | TNG605MT | TNG605-SKAMURNIBLRJ-MACRO | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-11 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0021933567 | 4200055400 | ATP000000288529 | #NAME? | Batch 4 & 5 | 02. FFT Scan Done, Continue |  | -6.2087 | 106.4283 | 2026-04-17 | 4
165 | FILTERING | TNG626 | Fix | TNG626 | TNG626-1 | 1 | 1 | R03 Jakarta & Banten | TNG626MT1 | E_TNG626_Cinyompok | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.217 | 106.5543 | 2026-03-09 | 3
166 | FILTERING | TNG626 | Fix | TNG626 | TNG626-2 | 2 | 1 | R03 Jakarta & Banten | TNG626MT1 | E_TNG626_Cinyompok | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID |  |  |  | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P2 | -6.217 | 106.5543 | 2026-03-09 | 3
167 | FILTERING | TNG664 | Fix | TNG664 | TNG664-3 | 3 | 1 | R03 Jakarta & Banten | TNG664MT1 | E_TNG664_Ptindosafety | DMT | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2231 | 106.5792 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
168 | FILTERING | TNG681 | Fix | TNG681 | TNG681-1 | 1 | 1 | R03 Jakarta & Banten | TNG681MT1 | E_TNG681_Pngarengannw | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232069 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P1 | -6.108 | 106.4853 | 2026-04-17 | 3
169 | FILTERING | TNG681 | Fix | TNG681 | TNG681-2 | 2 | 1 | R03 Jakarta & Banten | TNG681MT1 | E_TNG681_Pngarengannw | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232069 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P1 | -6.108 | 106.4853 | 2026-04-17 | 3
170 | FILTERING | TNG681 | Fix | TNG681 | TNG681-3 | 3 | 1 | R03 Jakarta & Banten | TNG681MT1 | E_TNG681_Pngarengannw | STP | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-09 | Irfan Kurniawan |  | ONSITE |  |  | TAGGING ISSUE | Standarisasi Jumper, Foto Site, Tower, Filter zoom N/a and Capture Cell Status, Cell Bandwidth, Board Status N/A | R03232069 |  |  |  | #NAME? | Batch#1 | 02. FFT Scan Done, Continue | P1 | -6.108 | 106.4853 | 2026-04-17 | 3
171 | FILTERING | TNG694 | Fix | TNG694 | TNG694-3 | 3 | 1 | R03 Jakarta & Banten | TNG694MT1 | E_TNG694M41_Kramatspt-NMM | STP | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled |  |  |  |  | SITE ID Unregistered in IOMS/INEOM | Not register IOMS, Pindah File Site List 8 April 2026 | AWAITING DATA | [5 empty] | #NAME? | Batch#5 | 02. FFT Scan Done, Continue | P3 | -6.0669 | 106.6102 | 2026-03-09 | 4 | Tidak bisa dijalankan Karena harus memakai data terupdate
172 | FILTERING | TNG701 | Fix | TNG701 | TNG701-2 | 2 | 1 | R03 Jakarta & Banten | TNG701MT1 | E_TNG701_Gintungmauk | STP | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain [ATP] | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.1224 | 106.551 | 2026-04-17 | 3
173 | FILTERING | TNG770 | Fix | TNG770 | TNG770-1 | 1 | 1 | R03 Jakarta & Banten | TNG770MT1 | E_TNG770_Binongpermai2-NDK | DMT | Not Registered | 10. DROP OUT | SITE ISSUE COMCASE | Site Issue :Minta THR 1jt | #NAME? | Cancelled |  |  |  | ONSITE | Need App AddCost-High Price | Pemilik lahan mememinta THR sebesar 1juta | AWAITING DATA |  | R03232530 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P1 | -6.2479 | 106.5845 | 2026-04-17 | 3
174 | FILTERING | TNG770 | Fix | TNG770 | TNG770-2 | 2 | 1 | R03 Jakarta & Banten | TNG770MT1 | E_TNG770_Binongpermai2-NDK | DMT | Not Registered | 10. DROP OUT | SITE ISSUE COMCASE | Site Issue :Minta THR 1jt | #NAME? | Cancelled |  |  |  | ONSITE | Need App AddCost-High Price | Pemilik lahan mememinta THR sebesar 1juta | AWAITING DATA |  | R03232530 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P1 | -6.2479 | 106.5845 | 2026-04-17 | 3
175 | FILTERING | TNG770 | Fix | TNG770 | TNG770-3 | 3 | 1 | R03 Jakarta & Banten | TNG770MT1 | E_TNG770_Binongpermai2-NDK | DMT | Not Registered | 10. DROP OUT | SITE ISSUE COMCASE | Site Issue :Minta THR 1jt | #NAME? | Cancelled |  |  |  | ONSITE | Need App AddCost-High Price | Pemilik lahan mememinta THR sebesar 1juta | AWAITING DATA |  | R03232530 |  |  |  | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P1 | -6.2479 | 106.5845 | 2026-04-17 | 3
176 | FILTERING | TNG828 | Fix | TNG828 | TNG828-3 | 3 | 1 | R03 Jakarta & Banten | TNG828MT1 | E_TNG828_Cengklong6-DMT | DMT | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.0873 | 106.6849 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
177 | FILTERING | TNG831 | Fix | TNG831 | TNG831-2 | 2 | 1 | R03 Jakarta & Banten | TNG831MT | E_TNG831_Grahapesona-NMM | STP | Registered | 1. Planning | NEED CAF | NEED CAF | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.253 | 106.5221 | 2026-04-17 | 4
178 | FILTERING | TNG850 | Fix | TNG850 | TNG850-2 | 2 | 1 | R03 Jakarta & Banten | TNG850MT1 | E_TNG850_Cengklongkosambi-PTI | PTI | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-07 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0013074974 | 9372/TC.03/EN-01/XI/2025 | ATP000000280184 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.0811 | 106.6851 | 2026-04-17 | 4
179 | FILTERING | TNG857 | Fix | TNG857 | TNG857-2 | 2 | 1 | R03 Jakarta & Banten | TNG857MT1 | E_TNG857_Cikupa2-DMT | DMT | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.232 | 106.5172 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
180 | FILTERING | TNG860 | Fix | TNG860 | TNG860-2 | 2 | 1 | R03 Jakarta & Banten | TNG860MT | E_TNG860_Perumahanmodernland-TBG | TBG | Registered | 1. Planning | NEED CAF | NEED CAF | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.1813 | 106.6372 | 2026-04-17 | 4
181 | FILTERING | TNG897 | Fix | TNG897 | TNG897-3 | 3 | 1 | R03 Jakarta & Banten | TNG897MT1 | E_TNG897_Cikupaindstng-DMT | PTI | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2046 | 106.5454 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
182 | FILTERING | TNG902 | Fix | TNG902 | TNG902-3 | 3 | 1 | R03 Jakarta & Banten | TNG902MT1 | E_TNG902_Urbanakarawacivillage-IBS | IBS | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-09 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | R03235225 | R0013075213 | 9372/TC.03/EN-01/XI/2025 | ATP000000280567 | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.2236 | 106.6051 | 2026-04-17 | 4
183 | FILTERING | TNX002 | Fix | TNX002 | TNX002-1 | 1 | 1 | R03 Jakarta & Banten | TNX002MT | E_TNX002_Mahkotasimprug-GTI | GTI | Registered | 1. Planning | NEED CAF | NEED CAF (GIHON) | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2402 | 106.7202 | 2026-04-17 | 4
184 | FILTERING | TNX010 | Fix | TNX010 | TNX010-1 | 1 | 1 | R03 Jakarta & Banten | TNX010MT | E_TNX010_Ciledugindahbarat-GTI | GTI | Registered | 4. Tpass Released | 1. NO ISSUE | CAF Release | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2202 | 106.6952 | 2026-04-17 | 4
185 | FILTERING | TNX010 | Fix | TNX010 | TNX010-2 | 2 | 1 | R03 Jakarta & Banten | TNX010MT | E_TNX010_Ciledugindahbarat-GTI | GTI | Registered | 4. Tpass Released | 1. NO ISSUE | CAF Release | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue |  | -6.2202 | 106.6952 | 2026-04-17 | 4
186 | FILTERING | TNX221 | Fix | TNX221 | TNX221-1 | 1 | 1 | R03 Jakarta & Banten | TNX221MT1 | TNX221M41_Benying-DMT | DMT | Registered | 9. Cancelled | DIALIHKAN KE DATA BARU |  | #NAME? | Cancelled | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#4 | 02. FFT Scan Done, Continue | P3 | -6.0856 | 106.5438 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
187 | FILTERING | TNX240 | Fix | TNX240 | TNX240-1 | 1 | 1 | R03 Jakarta & Banten | TNX240MT1 | E_TNX240_AeonmallbsdINDOOR-IBS | IBS | Registered | 4. Tpass Released | 1. NO ISSUE |  | #NAME? | Planning | [5 empty] | Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#3 | 02. FFT Scan Done, Continue | P3 | -6.3048 | 106.6423 | 2026-04-17 | 3
188 | FILTERING | BKS598 | Fix | BKS598 | BKS598-0 | 0 | 1 | R12 Eastern Jabotabek | BKS598MT1 | CIPINANGJAYA2DMT | DMT | Registered | 9. Cancelled | RESELLER TP | RESELLER TP | #NAME? | Cancelled |  |  |  | CANCEL |  | RESELLER TP, Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#2 | 02. FFT Scan Done, Continue |  | -6.2212 | 106.8818 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
191 | FILTERING | JKS778 | Fix | JKS778 | JKS778-0 | 0 | 2 | R03 Jakarta & Banten | JKS778MT1 | JKS778-TKPATRIOTISAT-MACRO | DMT | Registered | 9. Cancelled | RESELLER TP ISSUE | RESELLER TP CMI | #NAME? | Cancelled |  |  |  | ONSITE |  | RESELLER TP CMI, Pindah File Site List 8 April 2026, | AWAITING DATA | [5 empty] | #NAME? | Batch#2 | 02. FFT Scan Done, Continue |  | -6.3267 | 106.8118 | 2026-03-09 | 3 | Tidak bisa dijalankan Karena harus memakai data terupdate
195 | FILTERING | JKP203 | Fix | JKP203 | JKP203-3 | 3 | 1 | R03 Jakarta & Banten | JKP203HL1 | JKP203HT1_DIPONEGOROMENTENG2BTSH-DME_HT03 | DMT | Registered | 5. Permit Released | 1. NO ISSUE | Di Alihkan ke mitra lain | #NAME? | Planning | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | 106.8355 | -6.2006 | 2026-04-17 | 4
196 | FILTERING | JKP240 | Fix | JKP240 | JKP240-3 | 3 | 1 | R03 Jakarta & Banten | JKP240ME1 | JKP240MT1_DURI2_MT03 | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-23 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0022633088 | 5992/TC.03/EN-01/IV/2026 | ATP000000288811 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | 106.8048 | -6.1636 | 2026-04-17 | 4
197 | FILTERING | JKS068 | Fix | JKS068 | JKS068-2 | 2 | 2 | R03 Jakarta & Banten | JKS068IE1 | JKS068MT1_ITCFATMAWATI_MT02 | DMT | Registered | 5. Permit Released | 1. NO ISSUE | Site tidak ada di DMT. Masuk menggunakan TPass | #NAME? | RFS | 2026-04-23 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0022633094 | 5992/TC.03/EN-01/IV/2026 | ATP000000288819 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | 106.7985 | -6.2642 | 2026-04-17 | 4
198 | FILTERING | JKS123 | Fix | JKS123 | JKS123-3 | 3 | 2 | R03 Jakarta & Banten | JKS123MN1 | JKS123MT1_GRAHAMUTIARA_MT03 | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-16 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0022633159 | 5992/TC.03/EN-01/IV/2026 | ATP000000288820 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | 106.8081 | -6.2768 | 2026-04-17 | 4
199 | FILTERING | JKS134 | Fix | JKS134 | JKS134-2 | 2 | 1 | R03 Jakarta & Banten | JKS134IR2 | JKS134MT1_HTLMAHAKAM_MT02 | DMT | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Sudah di ambil TI dan RFS | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [5 empty] | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | 106.7955 | -6.2444 | 2026-04-14 | 4
200 | FILTERING | JKS509 | Fix | JKS509 | JKS509-1 | 1 | 1 | R03 Jakarta & Banten | JKS509ML1 | JKS509MT1_MSJDBBSSALAM_MT01 | DMT | Registered | 5. Permit Released | 1. NO ISSUE | Site tidak ada di DMT. Masuk menggunakan TPass | #NAME? | RFS | 2026-04-18 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0022633070 | 5992/TC.03/EN-01/IV/2026 | ATP000000288836 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | 106.8246 | -6.2165 | 2026-04-17 | 4
201 | FILTERING | JKT087 | Fix | JKT087 | JKT087-1 | 1 | 1 | R03 Jakarta & Banten | JKT087ME1 | JKT087MT1_MKRSRPERMAI_MT01 | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-18 | Denny Suhendra |  | ONSITE |  |  | TAGGING DONE | Need Capture Cell Status, Cell Bandwidth, Board Status N/A | NEED PDID | R0022633132 | 5992/TC.03/EN-01/IV/2026 | ATP000000288841 | #NAME? | Batch#6 | 02. FFT Scan Done, Continue | P2 | 106.8767 | -6.358 | 2026-04-17 | 4
202 | FILTERING | SRG671 | Fix | JSX365 | JSX365-2 | 2 | 1 | R03 Jakarta & Banten |  | E_JSX365_DelmankencanaBTSH-STP | STP | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Proses eATP dimitra lain | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-17 | 4
203 | RESCOPING | JSX898 | Fix | JSX898 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
204 | RESCOPING | JSX572 | Fix | JSX572 |  |  | 1 | R03 Jakarta & Banten |  | JSX572_Jltundaracilandak-IFT | IFT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-01 |  |  | ONSITE |  |  | TAGGING ISSUE |  | R03236840 |  |  |  | #NAME? | [5 empty] | 2026-04-16 | 3
205 | RESCOPING | JBX018 | Fix | JBX018 |  |  | 1 | R03 Jakarta & Banten |  | JBX018_PALEMRAJAUTAMAMWHW | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-01 |  |  | ONSITE |  |  | TAGGING ISSUE |  | R03236862 |  |  |  | #NAME? | [5 empty] | 2026-04-16 | 3
206 | RESCOPING | JBX062 | Fix | JBX062 |  |  | 1 | R03 Jakarta & Banten |  | JBX062_DURI KOSAMBI | TBG | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-01 |  |  | ONSITE |  |  | TAGGING ISSUE |  | R03236884 |  | 4200054007 |  | #NAME? | [5 empty] | 2026-04-16 | 3
207 | RESCOPING | JSX802 | Fix | JSX802 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 3
208 | RESCOPING | JSX832 | Fix | JSX832 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 3
209 | RESCOPING | JSX534 (P1) | Fix | JSX534 (P1) |  |  | 1 | R03 Jakarta & Banten |  | JSX534_PulorayapetogoganBTSH-IFT | IFT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-03-01 |  |  | ONSITE |  |  | TAGGING ISSUE |  | R03236845 |  |  |  | #NAME? |  |  | P1 |  |  | 2026-04-16 | 3
210 | RESCOPING | JPX338 (P3) | Fix | JPX338 (P3) |  |  | 1 | R03 Jakarta & Banten |  | JPX338_RelocStmicempakaputih-BMS | Unknown | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? |  |  | P2 |  |  | 2026-04-16 | 4
211 | RESCOPING | JKB585 (P2) | Fix | JKB585 (P2) |  |  | 1 | R03 Jakarta & Banten |  | JKB585_RelokRukoKebunJeruk | DMT | Not Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? |  |  | P3 |  |  | 2026-04-16 | 4
212 | RESCOPING | JKT368 | Fix | JKT368 |  |  | 1 | R03 Jakarta & Banten |  | JKT368 | IFT | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4 | (ACCEPTOR FROM JKT002)
213 | RESCOPING | JKB340 | Fix | JKB340 |  |  | 1 | R03 Jakarta & Banten |  | JKB340_CitraTower | DMT | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
214 | RESCOPING | JTX061 | Fix | JTX061 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
215 | COMBAT | COC611_CIANGSANA | Fix | COC611 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-01 |  |  | ONSITE |  |  | TAGGING ISSUE | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
216 | COMBAT | COC045_CIKAMPEK | Fix | COC045 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-01 |  |  | ONSITE |  |  | TAGGING ISSUE | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
217 | COMBAT | COC518_SETU | Fix | COC518 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-04-01 |  |  | ONSITE |  |  | TAGGING ISSUE | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
218 | COMBAT | COC260_BEKASI | Fix | COC260 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | On Going | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
219 | COMBAT | COC265_CIKAMPEK | Fix | COC265 |  |  | 1 | R03 Jakarta & Banten |  |  |  | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | On Going | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
220 | RESCOPING | JTX283 | Fix | JTX283 |  |  | 1 | R03 Jakarta & Banten |  | JTX283_JludowopondokgedeBTSH-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | On Going | 2026-04-01 | [5 empty] | AWAITING DATA | [5 empty] | #NAME? | [5 empty] | 2026-04-16 | 4
221 | FILTERING | JKS642 | Fix | JKS642 | JKS642-1 | 1 | 1 | R03 Jakarta & Banten | JKS642MT1 | JKS642-TJPERSADABRT-MACRO | STP | Registered | 10. DROP OUT | SITE ISSUE COMCASE | Comcase 200rb | #NAME? | Cancelled |  |  |  | ONSITE |  | KOMPENSASI 200RB, Pindah File Site List 8 April 2026, | AWAITING DATA |  | R03231690 |  |  |  | #NAME? | Batch#2 | 02. FFT Scan Done, Continue |  | -6.2993 | 106.8484 | 2026-04-30 | 4
224 | FILTERING | TGR365 | Fix | TGR365 | TGR365-1 | 1 | 1 | R03 Jakarta & Banten |  |  | DMT | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA | [7 empty] | 02. FFT Scan Done, Continue |  | 106.5501 | -6.2312 | 2026-04-30 | 4
225 | FILTERING | JTX676 | Fix | JKP754 |  |  | 1 | R03 Jakarta & Banten |  | E_JKP754_Jnctnhabang |  | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | On Hold | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
226 | FILTERING | RKB026 | Fix | JKP785 |  |  | 1 | R03 Jakarta & Banten |  | E_JKP785_Dukuhpinggir-STP | STP | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | On Hold | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
227 | FILTERING | SRG720 | Fix | JKS087 |  |  | 1 | R03 Jakarta & Banten |  | E_JKS087_CitragrahaINDOOR |  | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | On Hold | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
228 | FILTERING | SRG912 | Fix | JKS141 |  |  | 1 | R03 Jakarta & Banten |  | E_JKS141_Ambassador |  | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | On Hold | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
229 | FILTERING | TGR072 | Fix | JKS170 |  |  | 1 | R03 Jakarta & Banten |  | E_JKS170_Citibankpdindah-DMT | DMT | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | On Hold | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
230 | FILTERING | TNG134 | Fix | JKS747 |  |  | 1 | R03 Jakarta & Banten |  | E_JKS747_RssiloamsemanggiINDOOR |  | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Proses eATP dimitra lain | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
231 | FILTERING | TNG701 | Fix | JKU037 |  |  | 1 | R03 Jakarta & Banten |  | E_JKU037_Indstrsunter |  | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Proses eATP dimitra lain | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
232 | FILTERING | JBX199 | Fix | JUX217 |  |  | 1 | R03 Jakarta & Banten |  | E_JUX217_BukitmeditcasablancaBTSH-STP | STP | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | On Hold | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
233 | FILTERING | SRG054 | Fix | SRG054 | SRG054-1 | 1 | 1 | R03 Jakarta & Banten |  | E_SRG054_Htlferimerak |  | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Proses eATP dimitra lain | #NAME? | Cancelled | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
234 | FILTERING | TGR036 | Fix | JKS163 |  |  | 1 | R03 Jakarta & Banten |  | E_JKS163_Kompeximbank | DMT | Not Registered | 1. Planning | SITE-ID N/A IOMS |  | #NAME? | On Hold | [6 empty] | AWAITING DATA | [11 empty] | 2026-04-30 | 4
237 | FILTERING | JKU037 | Fix | JKU037 | JKU037-2 | 2 | 1 | R03 Jakarta & Banten |  | JKU037_4200052273 | DMT | Not Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Proses eATP dimitra lain | #NAME? | Cancelled | [6 empty] | AWAITING DATA |  | R03232535 | [9 empty] | 2026-04-30 | 4
240 | FILTERING | JTX676 | Fix | JTX676 |  |  | 1 | R03 Jakarta & Banten |  | JKP754_4200052273 | TBG | Registered | 1. Planning | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA |  | R03232680 | [9 empty] | 2026-04-30 | 4
241 | FILTERING | JBX199 | Fix | JBX199 |  |  | 1 | R03 Jakarta & Banten |  | JUX217_4200052176 | DMT | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Dialihkan ke MITRA lain | #NAME? | Cancelled | [6 empty] | AWAITING DATA |  | R03231767 | [9 empty] | 2026-04-30 | 4
242 | FILTERING | TNG605 | Fix | TNG605 | TNG605-1 | 1 | 1 | R03 Jakarta & Banten | TNG605MT1 | E_TNG605_Skamurniblrj | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.20868 | 106.4283 | 2026-05-05 | 5
243 | FILTERING | TNG594 | Fix | TNG594 | TNG594-3 | 3 | 1 | R03 Jakarta & Banten | TNG594MT1 | E_TNG594_Pasirnangka | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-05-07 | Denny Suhendra |  |  |  |  | TAGGING DONE |  | NEED PDID | R0023950497 | 9974/TC.03/EN-01/IV/2026 | ATP000000293367 |  |  |  |  | -6.2382 | 106.474 | 2026-05-05 | 5
244 | FILTERING | TNG508 | Fix | TNG508 | TNG508-3 | 3 | 1 | R03 Jakarta & Banten | TNG508MT1 | TNG508-TIGARAKSA-MACRO | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.28578 | 106.452 | 2026-05-05 | 5
245 | FILTERING | TNG014 | Fix | TNG014 | TNG014-2 | 2 | 1 | R03 Jakarta & Banten | TNG014MT1 | TNG014-RUKOSISKA-MACRO | TSL | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-05-07 | Denny Suhendra |  |  |  |  | TAGGING DONE |  | NEED PDID | R0023950489 | 9974/TC.03/EN-01/IV/2026 | ATP000000293466 |  |  |  |  | -6.16162 | 106.6636 | 2026-05-05 | 5
246 | FILTERING | SRG739 | Fix | SRG739 | SRG739-2 | 2 | 1 | R03 Jakarta & Banten | SRG739MT1 | Cilegonindah-DMT | DMT | Registered | 1. Planning | NEED CAF | DMT - EMA | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.043211 | 106.0689 | 2026-05-05 | 5
247 | FILTERING | SRG210 | Fix | SRG210 | SRG210-1 | 1 | 1 | R03 Jakarta & Banten | SRG210MT1 | E_SRG210M41_Mesjidpriyayikasemen-DMT | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.08448 | 106.1973 | 2026-05-05 | 5
248 | FILTERING | SRG207 | Fix | SRG207 | SRG207-1 | 1 | 1 | R03 Jakarta & Banten | SRG207MT1 | SRG207-PASULUHANWALANTAKADMT-MACRO | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.16837 | 106.2275 | 2026-05-05 | 5
249 | FILTERING | SRG031 | Fix | SRG031 | SRG031-1 | 1 | 1 | R03 Jakarta & Banten | SRG031MT1 | SRG031-CARENANG-MACRO | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.09072 | 106.323 | 2026-05-05 | 5
250 | FILTERING | JSX895 | Fix | JSX895 | JSX895-1 | 1 | 1 | R03 Jakarta & Banten | JSX895MT1 | JSX895-BPPKCAMATGABUN-MCME | DMT | Registered | 5. Permit Released | 1. NO ISSUE |  | #NAME? | RFS | 2026-05-06 | Denny Suhendra |  |  |  |  | WAITING LIST | [9 empty] | -6.33722 | 106.838 | 2026-05-05 | 5
251 | FILTERING | JSX813 | Fix | JSX813 | JSX813-2 | 2 | 1 | R03 Jakarta & Banten | JSX813MT1 | E_JSX813M41_Pasarcipete | TSL | Registered | 10. DROP OUT | DIALIHKAN KE MITRA LAIN | Sudah dikerjakan oleh Mitra lain | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.2603 | 106.8095 | 2026-05-05 | 5
252 | FILTERING | JSX716 | Fix | JSX716 | JSX716-2 | 2 | 1 | R03 Jakarta & Banten | JSX716MT1 | JSX716IL1_CIPUTRAWORLDGDG2DMT | DMT | Registered | 4. Tpass Released | 1. NO ISSUE |  | #NAME? | Planning | [6 empty] | AWAITING DATA | [9 empty] | -6.223051 | 106.8199 | 2026-05-05 | 5
252 | FILTERING |  | Fix | TNG116 | TNG116-2 | 2 | 1 | R03 Jakarta & Banten | TNG116MT1 | Cikuyatngrng-DMT | DMT | Registered | 1. Planning | 1. NO ISSUE
252 | FILTERING |  | Fix | TGR460 | TGR460-1 | 1 | 1 | R03 Jakarta & Banten | TGR460MT1 | E_TGR460M41_Jlgajahbarong-DMT | DMT | Registered
252 | FILTERING |  | Fix | TGR364 | TGR364-1 | 1 | 1 | R03 Jakarta & Banten | TGR364MT1 | Sindangsaritangerang-DMT | DMT | Registered
252 | FILTERING |  | Fix | SRG836 | SRG836-3 | 3 | 1 | R03 Jakarta & Banten | SRG836MT1 | Tenjoayu-DMT | DMT | Registered
252 | FILTERING |  | Fix | SRG282 | SRG282-1 | 1 | 1 | R03 Jakarta & Banten | SRG282MT1 | E_SRG282_Gunungsugihanyer-PST | PST | Registered
252 | FILTERING |  | Fix | SRG277 | SRG277-1 | 1 | 1 | R03 Jakarta & Banten | SRG277MT1 | SRG277-MELATIWARINGINKURUNGPST-MACRO | PST | Registered
252 | FILTERING |  | Fix | SRG073 | SRG073-1 | 1 | 1 | R03 Jakarta & Banten | SRG073MT1 | Bendungnclg2-DMT | DMT | Registered
252 | FILTERING |  | Fix | SRG029 | SRG029-2 | 2 | 1 | R03 Jakarta & Banten | SRG029MT1 | CIKANDEGABUS | DMT | Registered
252 | FILTERING |  | Fix | JKT088 | JKT088-1 | 1 | 1 | R03 Jakarta & Banten | JKT088MT1 | JKT088-JALANIRIAN-MACRO | DMT | Registered
252 | FILTERING |  | Fix | JKS264 | JKS264-3 | 3 | 1 | R03 Jakarta & Banten | JKS264MT1 | JKS264-GRAHASELARAS-MACRO | DMT | Registered

## INVENTORY REPORT
No. | Type | IN / OUT | Quantity | Material Description | Dilivery Date | Dilivery Note No | Purchecs Order Dilivery Date | Vendor Pengirim | Sender | Reciver
1 | Filter | IN | 56 | Dual Band Filter | 2026-02-06 | CMM0226/0055 | 4110006427 | CMM | M.HARYOKO | Iqbal
2 | Accesoris (Rubber) | IN | 56 | Accessoris (Rubber) | 2026-02-06 | CMM0226/0055 | 4110006427 | CMM | M.HARYOKO | Iqbal
3 | 4.3-10 to 4.3-10 | IN | 112 | 4.3-10 to 4.3-10 | 2026-02-06 | CMM0226/0055 | 4110006427 | CMM | M.HARYOKO | Iqbal
4 | 4.3-10 to DIN | IN | 112 | 4.3-10 to 4.3-10 | 2026-02-06 | CMM0226/0055 | 4110006427 | CMM | M.HARYOKO | Iqbal
5 | Filter | IN | 56 | Dual Band Filter | 2026-02-25 | CMM0226/0079 | 4110006427 | CMM | M.HARYOKO | Yoga
6 | Accesoris (Rubber) | IN | 56 | Accessoris (Rubber) | 2026-02-25 | CMM0226/0079 | 4110006427 | CMM | M.HARYOKO | Yoga
7 | 4.3-10 to 4.3-10 | IN | 112 | 4.3-10 to 4.3-10 | 2026-02-25 | CMM0226/0079 | 4110006427 | CMM | M.HARYOKO | Yoga
8 | 4.3-10 to DIN | IN | 112 | 4.3-10 to 4.3-10 | 2026-02-25 | CMM0226/0079 | 4110006427 | CMM | M.HARYOKO | Yoga
9 | Filter | IN | 123 | Dual Band Filter | 2026-02-26 | CMM0226/0080 | 4110006427 | CMM | M.HARYOKO | Yoga
10 | Accesoris (Rubber) | IN | 55 | Accessoris (Rubber) | 2026-02-26 | CMM0226/0080 | 4110006427 | CMM | M.HARYOKO | Yoga
11 | 4.3-10 to 4.3-10 | IN | 246 | 4.3-10 to 4.3-10 | 2026-02-26 | CMM0226/0080 | 4110006427 | CMM | M.HARYOKO | Yoga
12 | 4.3-10 to DIN | IN | 246 | 4.3-10 to 4.3-10 | 2026-02-26 | CMM0226/0080 | 4110006427 | CMM | M.HARYOKO | Yoga
13
14
15
16
17
18
19
20
21
22
23
24
25

## Status (hidden)
STATUS | Mitra TI | Implementasi Status | Lock Status | Registered
1. Planning | BMS | Awaiting | Waiting | Registered
2. Pending Confirmation | CMI | Scheduled | Confirm | Not Registered
3. Permit Submitted | Dhost | On Going
4. Waiting for TO Approval | DMT (Mitratel) | On Hold
5. Waiting for TP Approval | EBT | Ready For Service (RFS)
6. Permit & Tpass Released | IBS | Cancelled
7. Hold | Netwave
8. Cancelled | PTI (Protelindo)
STP
TBG